## Dark
PROJECT: 440 Database Project
Group 2 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | 2025-09-10 |  |  |  |  | September | [20 empty] | October | [27 empty] | November
Scrolling increment: | 5 | time axis 2025-09-15 to 2025-11-09
Milestone description | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Planning/ Design Phase
Form Groups | Goal | Instructor | 100% | 2025-09-15 | 1 | M: 2
Appoint Group Leader | Goal | Group | 100% | 2025-09-15 | 1 | M: 2
Schedule Group Meetings | Low Risk | Miguel | 75% | 2025-09-15 | 5
Create Gantt Chart | On Track | Miguel | 100% | 2025-10-04 | 2
Question Business Connect | On Track | Miguel | 100% | 2025-09-22 | 5
Create Business Rules | On Track | Miguel | 100% | 2025-09-22 | 5
Complete ERD | Med Risk | Nawal | 75% | 2025-09-22 | 20
Normalize ERD | High Risk |  | 50% | 2025-09-22 | 20
Data Dictionary | Low Risk |  | 50% | 2025-09-21 | 7
Development Phase
Construct Database In SQL Server |  |  |  | 2025-10-12 | 7
Test Database In SQL Server |  |  |  | 2025-10-12 | 7
Complete SQL Excercises |  |  |  | 2025-10-19 | 7
Replicate Database In MySQL |  |  |  | 2025-10-19 | 14
Test Database In MySQL |  |  |  | 2025-10-26 | 7
Create Web Application |  |  |  | 2025-10-26 | 14
Test Web Application |  |  |  | 2025-11-02 | 7
Evaluation Phase
Perfrom Final Testing |  |  |  | 2025-11-02 | 14
Create Presentation |  |  |  | 2025-11-02 | 14
Peer Review |  |  |  | 2025-11-02 | 14
Reflection |  |  |  | 2025-11-02 | 14
To add more data, Insert new rows ABOVE this one